## Slide 1: March 31, 2021 Work Group Update
FSWG
OGWG
RTOWG
TDWG
RHPWG
WESTAR/WRAP

## Slide 2
Educate.
Invest.
Plan.
Inspect.
Double check.
Learn Fire Safety Now.
Fire & Smoke Work Group Status Update October 2020 thru March 2021
Tasks / Coordination / Meetings
  Reformulated the WG under a new work plan scope
  WG calls – 2 meeting so far, scheduled monthly into the future
  Outreach – expand the WG to include more state, tribal and FLM members
  Ongoing meetings of the team working on the Conceptual Model for Long-term Fire Data Support
  Plan to send out a survey to get feedback on topics of interest (SMP, Exceptional Events, Rx to Wildfire nexus, Education, Outreach and Training)

## Slide 3: 12/1/2020 Board Approved Work Topics Fire & Smoke Work Group Progress Update
February/March 2021
  Activities to date –
    Kickoff call (Feb. 18)
    Conceptual Modeling (task 3)
    SMP map (task 1 & 5) proposed team to refine map and related information
  Tasks 2 & 4 to be discussed in future calls
  Update Workplan Scope
  Plan to hold teach-ins on topics of interest
  Work Group calls monthly into the future

## Slide 4: Oil & Gas Work Group Status Update October 2020 thru March 2021
Tasks / Coordination / Meetings
  Work Group calls (Every four months; call held March 30, 2021)
    Recurring Topic: Roundtable
      State/Local/tribe: Initiatives/Rulemaking/Legislative changes; Regional Haze and/or Ozone SIP-related analyses related to Oil & Gas
      Federal: Initiatives/Rulemaking/Legislative changes; Initial thoughts on Regional Haze submittals to date related to Oil & Gas
    Other Topics:
      Mar. 2021 (upcoming)
        WRAP Region Oil & Gas: Recent Activity Trends and Emission Inventories
        Emissions Inventory:
          2017 Outline – Strengths/Weaknesses for Western Modeling Platform (Ramboll)
          2020 NEI Development Plan (EPA)
      Oct. 2020
        CARB Report on Venting, Fugitive, and Flaring Emissions from Natural Gas
        2014 Colorado Model Evaluation Database Package (EPA)
  Coordination with contractor (infrequent)

## Slide 5: 12/1/2020 Board Approved Work Topics Oil & Gas Work Group Progress Update
February/March 2021
  Update Workplan Scope
  Kickoff call: TBD
  Work Group calls
    Mar. 30, 2021
    Aug. 10, 2021

## Slide 6: Regional Technical Operations Work Group Status Update October 2020 thru March 2021
Tasks / Coordination / Meetings
  RepBase2 and 2028OTBa2 simulations for estimating reasonable progress goals (RPG) using three different methods, recommend using ‘EPA wo fire’ approach
  Regional source apportionment run for use in adjusting glideslopes to account for anthropogenic emissions and prescribed wildland fire
  Dynamic model evaluation to assess regional air quality model’s response to changes in US anthropogenic emissions for 2002, present day (2014-2018), and 2028
  Model verification study of 2014v2
  Workgroup calls: 12/16/20 and 3/2/21
  Weekly coordination calls with modeling contractor (Ramboll)
  Documents: Procedures for Making Visibility Projections and Adjusting Glidepaths using the WRAP-WAQS 2014 Modeling Platform (3/1/21)
  Transfer of regional haze results to TSS and modeling files to IWDW
  By state and source group apportionment run

## Slide 7: 12/1/2020 Board Approved Work Topics RTO Work Group Progress Update
February/March 2021
  Discuss with RTOWG to refine work topics
  Update Workplan Scope
  Kickoff call
  Topical discussion / roundtable
  Internal and External coordination / topics
  Coordination with contractor
  Work Group calls

## Slide 8: Tribal Data Work Group
Status Update (Past 6 Months)
  Completed RH Workplan tasks in Summer 2020
  No additional meetings due to lack of bandwidth from COVID-19 Pandemic disruptions
Progress Update (Next 6 Months)
  Update the Tribal Contacts list made in 2019
  Identify needs from WRAP Board Approved Work Topics
  Work with TSC and other Work Groups to support tribal representation

## Slide 9: Regional Haze Planning Work Group Status Update October 2020 thru March 2021
Modeling Results Meetings
  November – March
  Next April 1st
State-State coordination call
  April 13th

## Slide 10: 12/1/2020 Board Approved Work Topics RHP Work Group Progress Update
Currently nothing identified for RHPWG to assist with

## Slide 11: 12/1/2020 Board Approved Work Topics WESTAR/WRAP Progress Update
12) Conceptual Model for Long-Term Fire Data project: itemizing remote sensing inputs for annual fire EIs
13) Proposal not selected by NASA for funding
14) Formation of small sensors subgroup to the WESTAR Technical Committee