## Slide 1: WRAP TSC/Co-Chairs Call Workplan Progress Update September 26, 2018
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Tribal Data Work Group
Co-Chairs: Kris Ray (Colville Tribes) and Emma Ruppell (Bishop Paiute Tribe)
Call Schedule: as needed
Website: http://www.wrapair2.org/tdwg.aspx (under development)
Current Tasks/Projects
  Working on the Tasks in the 2018 to 19 workplan
  Data analysis
  Outreach

## Slide 4: Tribal Data Work Group Work Products and Next Steps
TDWG Road Map Scope of Work (Institute for Tribal Environmental Professionals)
  General WRAP outreach, contact list, and map updating
  Tribal AQS data gap study
  Tribal NEI data gap study
  Tribal oil and gas EI studies
  Consultation Protocol
  WRAP webinars
Next Steps
  Kick-off call
  Leverage ITEP work to connect with National Tribal Air Monitoring Support Center and National Tribal Air Association
  Most products completed within 10 week of contract

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Fire & Smoke Work Group
Co-Chairs: Sara Strachan, Josh Hall
Call Schedule: monthly
Website: http://www.wrapair2.org/FSWG.aspx
Current Tasks/Projects
  2014 WRAP FNEI data review
  National 2016 Emissions Modeling Platform – Fires WG support for WRAP region
  Steady update/maintenance work on WRAP FETS website and database

## Slide 7: Status Report for Fire & Smoke Work Group
  Approach: 4 tasks in 2018-19 by Air Sciences, Inc. (contracted work)
    evaluation of the 2014 NEI, evaluation of adjustments for sensitivity testing, and evaluation of usefulness of 2016 EPA inventory effort for understanding the role of fire;
    using year specific inventory to develop inventory representative of 5-year baseline;
    scaling the representative inventory for sensitivity testing; and
    updating the Fire Emissions Tracking System (FETS)
  Status
    Next FSWG call scheduled October 29
  Milestones
    Align with modeling input file milestones
  Coordination and Next Steps
    Oct. 17 deadline for 2014 FNEI feedback
    Oct. 29 call

## Slide 8: Status Report for Fire & Smoke Work Group
2014 WRAP FNEI data review
  Approach
    Build an evaluation framework for states/tribes to review inventory
    Follow up individually as needed to solicit feedback
    Summarize results in a memorandum with recommendations for holistic inventory updates
  Status
    Evaluation tool and background documents distributed to state experts and state RH contacts
    Engaging with feedback, troubleshooting access issues
  Milestones
    Oct. 17, 2018 – feedback due
  Coordination and Next Steps
    Incorporate feedback into inventory
    Coordinate with modelers about format
    Decide about new SCC categories to include, plume rise algorithm, pile burning, etc.

## Slide 9: Status Report for Fire & Smoke Work Group
2016 Platform Fire NEI data review
  Approach
    Participate in fire workgroup process
    Apply 2014 evaluation framework to beta version (2016b)
    Draft recommendations for national fire workgroup based on evaluation
  Status
    Some western states and tribes contributed data to beta inventory (ID, Nez Perce, WA, CO)
    Jeff Vukovich gave status summary of beta inventory progress on Sept. 24 call
  Milestones
    Q3 2018 – apply evaluation framework to 2016b
    Expect to have recommendations by December 2018
  Coordination and Next Steps
    Continue participation in fire workgroup monthly calls
    Consider having George Pouliot present Ag fire emissions processing to FSWG

## Slide 10: Oil and Gas Work Group
Co-Chairs: Amanda Brimmer, Mark Jones, and Darla Potter
Call Schedule:
  OGWG - 2nd Tuesday, every other month @ noon MT
    October 9, 2018
    December 11, 2018
  OGWG Project Management Team (PMT) Calls – as needed
    September 10, September 28
Website: https://www.wrapair2.org/OGWG.aspx
Current Tasks/Projects
  Road Map Phase II:
    Task 1: 2014 Base Year O&G Emissions Inventory
    Task 2: 2028 Forecast O&G Emissions Inventory (based on 2023)
      will include on-the-books (OTB) and on-the-way (OTW) controls

## Slide 11: Status Report for Oil and Gas Work Group
Task 1: 2014 Base Year O&G Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status/Deliverables
Inventory Compilation, Reconciliation, Data Gaps | Spreadsheet* + WG Discussion 8/14
2014 O&G Activity | Spreadsheet* + WG Discussion 8/14
Identify Emission Factors and Speciation Profiles for Oil and Gas Sources | PMT Discussion 8/20
State and industry survey | PMT Discussion 9/10 & 28
Technical Improvements and Reporting | PMT Discussion 8/20
SMOKE-ready Emission Inventory Files | No work yet
Milestones: | 
Sept. 2018 – Literature review PowerPoint | 
Oct. 2018 – Survey finalized to send out | 
Apr. 2019 – SMOKE-ready 2014 O&G emissions inventory files | 
Coordination and Next Steps: | 
Assistance needed from States to complete survey (coordinate with local industry if needed) | 
OGWG and Project Management Team (PMT) review of draft work products | 
* Posted on OGWG webpage

## Slide 12: Status Report for Oil and Gas Work Group
Task 2: Forecast 2028 (OTB & OTW Controls) Oil & Gas Emissions Inventory | 
Approach: Contractor (Ramboll) performing work on following tasks: | Status
Identify historic growth, supply, demand, and production decline | No update
Identify a Range of Forecast Year Oil and Gas Scenarios | “
Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | “
Implement Regionally-Consistent 2028 Forecast (OTB & OTW controls) Emissions Inventory | “
SMOKE-ready Emission Inventory Files | “
Milestones: | 
May 2019 – Final Report | 
June 2019 – SMOKE-ready 2028 O&G emissions inventory files | 
Coordination and Next Steps: | 
OGWG and Project Management Team (PMT) review of draft work products | 

## Slide 13
Regional Technical Operations Work Group

## Slide 14: RTOWG Work Group
Co-Chairs:
  Gail Tonnesen (EPA R8)
  Kevin Briggs (CO CDPHE)
  Mike Barna (NPS ARD)
Call Schedule:
  Previous workgroup call: 9/20/18
  Next workgroup call: 10/18/18
  RTOWG co-chairs participating in other workgroup calls
    RHPWG
    RHPWG Emissions & Modeling subcommittee
Website:
  http://www.wrapair2.org/RTOWG.aspx

## Slide 15: Status Report for RTOWG
Presentation from Mark Zondlo (Princeton) “Ammonia in Colorado: insights from in-situ, mobile, and satellite”
  Mark has a NASA HAQAST project to study ammonia
  New tools to 1) evaluate emission inventory development and 2) model performance (both regional and global)
Overview of Emissions Inventory and Modeling Protocol Subcommittee’s 2014 NEI v2 data review results
EPA presentation of 2016 modeling platform to MJO’s
  H-CMAQ v. GEOS-Chem
EPA Regional Haze Reform Road Map overview

## Slide 16: Motivation
Reactive nitrogen deposition in Rocky Mtn. Natl.. Park.
• 3 kg N ha-1 yr-1 critical load
• 3.65 kg N ha-1 yr-1observed
• NH3 dry deposition modeled at 20% of total
(Bowman et al., 2012; Benedict et al., 2013)
NH3 in Colorado
• CAFOs 68% of NH3 in CO (NEI, 2011)
• 2-60% losses within 2 km of farm in CA (Loubet et al., 2009)
Challenges
• NH3 incredibly difficult to measure
- low mole fractions (~ pptv-ppbv)
- large dynamic range / short lifetime
- sampling problems (inlets, phase)
Where is the NH3 coming from? What are spatiotemporal variations?
How can in-situ and remote sensing measurements at vastly different scales be synthesized for a broader understanding?
From Mark Zondlo’s 9/20/18 presentation to RTOWG

## Slide 17: AMoN and IASI comparison in Colorado
Selecting IASI and AMoN observations for the comparison (2008 – 2015):
  4 AMoN sites in Colorado located near Gothic, Fort Collins, RMNP Longs Peak, RMNP Loch Vale
  Spatially confined to 25 km
  Averaging IASI data for AMoN sampling period
  Valid IASI data covering 50% of the time
AMoN and IASI show moderate correlation, stronger
in regions of higher NH3
From Mark Zondlo’s 9/20/18 presentation to RTOWG

## Slide 18
Regional Haze Planning Work Group

## Slide 19
Co-Chairs: Tina Suarez-Murias (CARB) & Jay Baker (UT DEQ)
Call Schedule: 1st Tuesday every even month, noon-2PM Mountain Time
Website: https://www.wrapair2.org/RHPWG.aspx
Current Activities:
  All related to State Regional Haze SIP preparation, tasks in 2018-2019 Work Plan, and training with SIP preparation tools
  Presentation to Air Directors at WESTAR Business Council September 19, 2018
  Upcoming bi-monthly call on October 2, 2018
  Special Webinar on TSSv.2 - Friday, October 5, 1:00-2:30 PM Mountain Time
Regional Haze Planning Work Group
Notes: The Work Group is lengthening its bimonthly call to 2 hours. As a matter of necessity, the large Work Group is evolving into a classroom where everyone is brought up to speed for SIP preparation.
The smaller subcommittees and other Work Groups and contractors are developing products, tools, and deliverables needed to write the SIPs.
As we start to roll out some of the tools, etc. we may have additional meetings, depending on the complexity of the items we need to explain.

## Slide 20
  EPA “Road Map” posted September 11, 2018
    Principles: States have lead in program implementation & EPA will help
    EPA Rule Revisit will go to Public Notice in future
    EPA Final Guidance released in stages
      Most Impaired Days (MID) selection Fall 2018
      Revised Natural Conditions
      Modeling Platform Summer 2019
      Control Analysis might include visibility impact factor
    Some FIPs replaced with SIPs
Regional Haze Planning Work Group
Notes: The Work Group is lengthening its bimonthly call to 2 hours. As a matter of necessity, the large Work Group is evolving into a classroom where everyone is brought up to speed for SIP preparation.
The smaller subcommittees and other Work Groups and contractors are developing products, tools, and deliverables needed to write the SIPs.
As we start to roll out some of the tools, etc. we may have additional meetings, depending on the complexity of the items we need to explain.

## Slide 21
Regional Haze Planning Work Group

## Slide 22: Regional Haze Planning Work Group Control Measures Status Report
Approach
  Develop Protocols for States to use to target emissions reductions from Non-Mobile Anthropogenic Sources within their State
  Develop means to demonstrate these reductions improve visibility in Class I Areas
Status
  Interpret EPA proposed guidance for 80% of non-mobile anthropogenic sources (facility/unit/source category)
  Propose screening tools (e.g. Emissions/Distance threshold from Class I Area Q/d > x; source emissions Q > y TPY)
  Utilize WRAP/WEP
Milestones
  Develop and circulate schedule for States’ input to other Work Groups and contractors (pending)
  Draft WRAP Reasonable Progress Source Identification and Analysis Protocol to be shared with RHPWG
Coordination and Next Steps
  Circulate Screening Techniques “menu” as working draft to states for use as guidance selecting “target sources”
  Review four-factor methods and options
  Work with other Work Groups on multi-year emissions averaging if needed for cost-benefit analysis or modeling
  Reconcile Area Source Emissions categories vs. Stationary Source facilities with multiple units for control analysis
  Determine needs for contractor assistance
Notes: -Control Measure subcommittee is reviewing a draft screening techniques protocol. Although subcommittee members are adding to it now, it will remain a Working Draft when released. It will describes a menu of techniques that states can use to select sources for which a four-factor analyses can be applied.
-For screening to identify potential sources for further review states can use:
  Existing tools, such as the existing Land Use maps from the Causes of Haze, accessible through the TSSv.1 webpage
  Future Weighted Emissions Potential or WEP, that results from modeling
  Q/d or emissions over distance – which may be more or less than 10, depending on the state geography
-Next steps are to work on the four-factor method and differentiate between point and area sources.

## Slide 23: Regional Haze Planning Work Group Emissions Inventory & Modeling Protocol Status Report
Approach
  Collect and collate emissions data from all states (2014 and future forecasts)
  Photochemical modeling for CONUS western states
Status
  All states have verified 2014 data, some still making adjustments
  Photochemical modeling contract reviewed before release
Milestones
  Identified categories needing further attention (unpaved road dust, unreported minor sources)
  Considering categories to be grouped for source apportionment (e.g. residential woodsmoke)
Coordination and Next Steps
  Set deadline to grid out 2014 inventory for regional photochemical modeling
  Work with RTO Work Group to secure contractor for baseline and future year modeling
  Get 2014 data from Oil & Gas and Fire & Smoke Work Groups model-ready by Spring 2019
  Coordinate with Fire & Smoke Work Group on multi-year averages to use for future year modeling
Notes: This subcommittee has not met since the last TSC meeting.
Members are chasing down emissions inventories from states that have not confirmed or changed their 2014 inventories
Several members are also on the RTO Work Group and are working on modeling protocols with that group.

## Slide 24: Regional Haze Planning Work Group Shared Database Status Report
Approach
  Assure that publically accessible database has useful information for states to use in SIP preparation
  Work with CIRA contacts to share state needs and evaluate design of TSS v.2
Status
  Reviewing presentation options for monitoring data
  Comments compiled for CIRA collaborator’s monthly response
Milestones
  Reviewing graphical comparison of haziest and most impaired days
  TSS v.2 Progress Report Webinar for future users scheduled for October 2018
Coordination and Next Steps
  Developing a trend tool to allow states to assess 2000-2016 monitoring data trends with MID relative to revised Glide Path
  Assist with development of Glossary for TSS v.2
  Coordinating with Monitoring Subcommittee regarding the visualization tool and will coordinate with Emissions and Modeling subcommittee regarding additional functionalities
Notes: The Shared Database Subcommittee is working with the contractors at Colorado State on Technical Support System v2. with the hope of presenting it to the Regional Haze Work Group at the October 2 Conference Call of the Regional Haze Work Group.
They caution that the algorithms behind the display might change the final values displayed as the Monitoring and Glide Path subcommittee and the contractors verify the input values.
Some data patching and substitution may be needed at some monitors, if they do not have a complete year that is critically needed.

## Slide 25: Regional Haze Planning Work Group Monitoring Data & Glide Path Status Report
Approach
  Evaluate proposed EPA tracking metric with alternative extreme episodic event (E3) thresholds and other options for selecting the 20% Most Impaired Days (MID) in the west
  Set up Excel spreadsheet and R code analysis to test variables on 26 representative IMPROVE sites
  Each State can use these R and Excel tools to analyze their IMPROVE sites using FED dataset
Status
  Prepared draft list of alternative approaches to MID metric with pros and cons for each and working on
  Preparing documentation of the analytical approaches evaluated
  Continue to review ongoing analyses of data by IMPROVE Committee and Federal Agencies
Milestones
  Evaluation data and tools posted for wide review
    https://azdeq.sharefile.com/d-s3e0afe94b844e70a
  Contractor to prepare report documenting data patching and data substitution
Coordination and Next Steps and Tasks
  Present findings to TSC and then to SIP/TIP writers through RHPWG
  Draft Report for feedback from RHPWG (all states, FLMs, tribes, EPA)
  Evaluate changes to redo Baseline and adjust 2064 Natural Conditions (Glide Path slope and endpoints)
  Consider tools that might help differentiate natural and anthropogenic sources
Notes: The Monitoring Subcommittee encourages all to review the R and Excel tools they have developed to compare methods to calculate Most Impaired Days for each state’s IMPROVE monitors.
Next on the agenda is reviewing Natural Conditions and redoing the baseline.
Any recommendation for a single MID process will be presented to the TSC and then the Regional Haze Work Group.
Coordinating with the Shared Database Subcommittee.

## Slide 26: Regional Haze Planning Work Group Consultation and Coordination Status Report
Approach
  Recommend framework for State/State, State/Local Air Agency, State/ FLM consultation and for coordination with EPA and Tribes
  Potential ideas for future communication and outreach with stakeholders & the public
Status
  Updating webpage with links to key resources for states/locals/tribes
  Drafting timeline that recommends occasions for informal consultation during SIP development
Milestones
  List of contacts at all agencies for informal conversations during SIP development and for formal review of draft SIPs posted on webpage, to be updated later this year with list of tribal contacts from TDWG
  General Contract ($25,000) includes formal consultation requirements related to states’ public review procedures & schedules (State SIP Readiness)
Coordination and Next Steps
  Coordinate with subcommittees on timing of final work products
  Review recommended tiered approach to consultation and timeline of informal consultation junctures
  Draft white paper that provides the “how,” including consultation/coordination protocols (e.g. for state/local air agency coordination on control measures and state/state negotiation regarding upwind state reductions)
Notes: The Consultation and Coordination Subcommittee is completing their list of contacts and working on a white paper that will link consultation to key points in the SIP development process.
New contacts from the Forest Service and the Fish and Wildlife Service and EPA have just joined the Subcommittee.