## Slide 1: Monthly Update on 2018-2019 WRAP Workplan January 30th, 2019 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2
Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Worked with ITEP and EN3 on the contracted tasks
  Documents are available on the RH TDWG page in draft form
Workplan Tasks for the Next Two Months
  Schedule webinar dates
  Organize WRAP and TDWG participation at the National Tribal Forum on Air Quality
  Finalize all products from the ITEP and EN3 work at next TDWG Call

## Slide 4: Workplan Coordination Activities by Tribal Data Work Group
Workplan Coordination Occurring over the Last Month
  Consultation & Coordination (C&C) Subcommittee – ITEP, EN3 and TDWG, how does our products fit into framework document and scheduling of webinars
  Oil and Gas Workgroup – ITEP, EN3 and TDWG drafted Tribal oil and gas related emissions
Workplan Coordination Needed over the Next Two Months
  Same groups as mentioned above
  National Tribal Forum on Air Quality – breakout session and networking clubhouse organization
  EPA for the WRAP area Tribal contact list

## Slide 5
Fire and Smoke Work Group
and

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Provided draft workplan update to workgroup prior to deadline
  Received zero feedback from workgroup
  Submitted workplan update to Frank anyway
Workplan Tasks for the Next Two Months
  Finalize workplan update
  Submit base year Fire EI to Ramboll ✔
  Scheduled call: Utah Smoke Management Plan presentation
  Identify methodologies to determine future year and multi-year baseline fire emissions for RH modeling

## Slide 7: Workplan Coordination Activities by Fire and Smoke Work Group
Workplan Coordination Occurring over the Last Month
  None.
Workplan Coordination Needed over the Next Two Months
  Need to coordinate with Emissions Inventory and Modeling Protocol Subcommittee and RTOWG on preparing the baseline and future year fire EIs

## Slide 8
Oil and Gas Work Group

## Slide 9: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG Survey deliverables for O&G operator distribution by State Agencies
  Draft OGWG Workplan Review & Update out for review for Jan. 22 call
Workplan Tasks for the Next Two Months
  OGWG O&G Operator Surveys – Late February - Completion
  Task 1: Base Year Inventory - Late February - Survey compilation memo
  Task 2: Forecast 2028 Inventory (On-the-books controls) - February - Forecast scenarios

## Slide 10: Workplan Coordination Activities by OGWG
Workplan Coordination Occurring over the Last Month
  January 9 Project Management Team & S,L,T Agencies Call
    Check-In OGWG Survey
  Assistance from Agencies on OGWG Survey distribution to O&G operators
  January 22 OGWG Special Call
    Mid-Course Workplan Review & Update
Workplan Coordination Needed over the Next Two Months
  February 12 OGWG Bi-Monthly Call
    Agenda under development
  Assistance from Agencies / O&G operators to complete OGWG Survey
  OGWG and PMT review of draft work products

## Slide 11
Regional Technical Operations Work Group

## Slide 12: Workplan Progress RTOWG
Workplan Progress over the Last Month
  Western Modeling Shakeout Coordination call with Contractors on January 2
  Monthly RTOWG Call on January 11th
    2014 Shakeout Western Modeling project deliverables and progress report
    NPS/CIRA project to apply 2014 western modeling platform to focus on NH3 simulation and improvement
    Plans for updates to the RTOWG portion of the Workplan
Workplan Coordination Occurring over the Previous Month
  RTOWG Co-Chairs Participated in the:
    RHPWG call on January 8
    O&G WG Workplan call on January 22
Workplan Coordination over the Next Two Months
  Updated 2014 Base Year Emission Inventory from the RHPWG-EI MP
  Next RTOWG Workplan call is January 31 at 10:00-10:30 MST
  Next “Shakeout” call with contractors is January 31 at 2:00-3:30 MST
  Next Regular Monthy RTOWG call is February 12 at 10:30-12:00 (subject to change)

## Slide 13: Workplan Tasks for the Next Two Months: 2014 Platform Development and Shake-Out Study.
Work Item | Draft | Final
Phase I 2014 Shake-Out Modeling Plan | Dec 2018 | Jan 2019
Single-Source Visibility Modeling Webinar | Dec 2018 | Dec 2018
Single-Source Visibility Modeling Memorandum | Jan 2019 | Feb 2019
2014 Emission Inputs | Jan 2019 | Feb 2019
2014 36-km CONUS Domain Boundary Conditions | Jan 2019 | Jan 2019
2014 Meteorological Inputs | Jan 2019 | Jan 2019
2014 WRF and Biogenic PGM Sensitivity Tests | Feb 2019 | Feb 2019
2014 Annual CAMx and CMAQ Platforms | Feb 2019 | Feb 2019
Phase II Illustrative Modeling Plan (WAQS/WestJumpAQMS) | Feb 2019 | Mar 2019
2014 Annual CMAQ and CMAQ Base Case and MPE | Mar 2019 | Mar 2019
Transfer 2014 Platform to IWDW | Feb 2019 | Mar 2019
2014 Shake-Out Close-Out Meeting | Mar 2019 | Mar 2019
2014 Shake-Out Report | Mar 2019 | Mar 2019

## Slide 14
Regional Haze Planning Work Group

## Slide 15: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  Finished SIX “White Papers” (Subcommittee Deliverables)
  Will circulate as “drafts” to help SIP writers & other Work Groups pending Federal partners returning for consensus & docketing
  Provided Updates & Revisions to 2018-2019 Work Plan for first draft
Workplan Tasks for the Next Two Months
  See Subcommittee reports
  Discern Training & Outreach Needs for New Over-Arching Task 6
  Get Consensus for WorkPlan revisions and Updates

## Slide 16: Workplan Coordination Activities by Regional Haze Planning Work Group
Workplan Coordination Occurring over the Last Month
  TSC conference call in December
  Individuals sit on other Work Group calls
  Increase Work Group conference calls to once a month in 2019
Workplan Coordination Needed over the Next Two Months
  Better exchange of information with RTOWG on forecasting and modeling
  Refocus on training and outreach (coordinate with C&C and SDb)
  Work closely with TSC, Subcommittees, and States to understand what contracting can be funded; what Subcommittees can reasonably be expected to do; what states must do on their own
  Identify gaps between feasible deliverables and needs/expectations of State SIP writers

## Slide 17: RHPWG EI & MP Subcommittee
Workplan Progress over the Last Month
  Provided state emissions updates to contractor for base-year “shakeout” modeling
    Emissions Processing underway
Workplan Tasks for the Next Two Months
  Final review for base-year EI White Paper on Jan 31
    Will forward for docketing after subcommittee comments are collected
  Review “shakeout” emissions summaries from contractor
  Prepare for second round of base-year modeling
    Point source representativeness?
Subcommittee Coordination
  Work with modeling contractor Ramboll (past & future)
  Coordinate through WGs or contractor for O&G or F&S inventory data? (future)
  Coordinate with RTOWG on categories for Source Apportionment

## Slide 18: RHPWG MD & GP Subcommittee
Workplan Progress over the Last Month
  Finished White Paper on Most Impaired Days Selection
  Webinar with EPRI on International Emissions for 2064 endpoint adjustment ideas
Workplan Tasks for the Next Two Months
  White Paper to Work Group membership as “draft” pending return of Federal partners for consensus and docketing
  Awaiting ARS completion of Data Substitution and Patching
Subcommittee Coordination
  Members participate heavily in SDb Sc (past & future)
  Increased coordination with RTOWG and EI & MP Sc to determine methods for international transport URP adjustment (future)
  May increase interaction with EPA and with IMPROVE Subcommittee to develop method for determining Glide Path 2064 endpoint (future)

## Slide 19: RHPWG CM Subcommittee
Workplan Progress over the Last Month
  Finished Screening Guidance White Paper
  Finalized contract for Q/d screen and priorities for culling 4-factor analysis candidates
Workplan Tasks for the Next Two Months
  White Paper to Work Group membership as “draft” pending return of Federal partners for consensus and docketing
  Distribute results of contractor screening perhaps as webinar
  Further Discussions of Area Sources and four-factors
  Further Discussions of Visibility as a factor if states still considering it
Subcommittee Coordination
  Work with Q/d contractor Ramboll (past & future)
  Coordinate with C&C Sc for Webinar on source screening process using contractor deliverable (future)
  Coordinate with O&G WG will Q/d contract pick up O&G sources in every state; can be area or stationary (future)

## Slide 20: RHPWG C&C Subcommittee
Workplan Progress over the Last Month
  White Paper for three-tiered “Framework” finished pending coordination with TDWG on additional description of informal consultation with tribes
Workplan Tasks for the Next Two Months
  White Paper to Work Group membership as “draft” pending completion and return of Federal partners for consensus and docketing
  Complete timeline of key milestones for states
  Begin work on “new” outreach task
  First coordination webinar postponed to March
Subcommittee Coordination
  Work with TDWG and ITEP on “coordination” contacts (past & future)
  Coordinate with SDb Sc on new “training & outreach” task (January and beyond)
  Work with all Subcommittees and Work Groups to determine which has deliverables to showcase in first quarterly regional haze webinar (future)

## Slide 21: RHPWG SDb Subcommittee
Workplan Progress over the Last Month
  Finished Overview of SIP Process White Paper
  Working on In formational/Instructional text for TSS v.2.
Workplan Tasks for the Next Two Months
  White Paper to Work Group membership as “draft” pending return of Federal partners for consensus and docketing
  Begin work on “new” outreach task
Subcommittee Coordination
  Work with CIRA as sounding board for TSSv.2 development (past & future)
  Coordinate with C&C Sc on new “training & outreach” task (January and beyond)
  Work With C&C subcommittee to coordinate Webinar timing for periodic “Progress Reports” on TSS v.2 functionalities

## Slide 22
End of Workplan Progress Update

## Slide 23: Workplan Progress by (insert name) Work Group
Workplan Progress over the Last Month
  Example bullets
  Draft report out for review
  Provided feedback to contractor regarding IMPROVE data substitution
Workplan Tasks for the Next Two Months
  Example bullets
  Finalize draft report
  Review final contractor recommendations on data substitution

## Slide 24: Workplan Coordination Activities by (insert name) Work Group
Workplan Coordination Occurring over the Last Month
  Who did you coordinate with, what topics were discussed, and when did it occur (replace this text with you own)
Workplan Coordination Needed over the Next Two Months
  What activities do you need to coordinate on, with whom, and expected timeframe (replace this text with you own)