## Slide 1: Monthly Update on 2018-2019 WRAP Workplan February 26th, 2020 TSC and Work Group Co-Chairs Call
Tribal Data WG
Fire and Smoke WG
Oil and Gas WG
Regional Technical Operations WG
Regional Haze Planning WG

## Slide 2: Tribal Data Work Group

## Slide 3: Workplan Progress by Tribal Data Work Group
Workplan Progress over the Last Month
  Participation letter draft reviewed & adopted by TDWG
  EN3 Oil & Gas Report final draft addressing comments from OGWG; comments and report/revisions reviewed & adopted by TDWG; updated web list of projects for completion
  TDWG review of 2020 ITEP SOW
Workplan Tasks for the Next Two Months
  Distribute letter using new tribal contacts email for WRAP
  Docket approved OG report, any other remaining reports
  Draft 2020 TDWG Workplan section/appendix- discuss on next call

## Slide 4: Proposed Future Projects - TDWG
  SOW for 2020 work provided by ITEP; discussion on TDWG calls of focus for 2020 activity: technical assistance for tribes with state SIP (or related) reviews
  Continued updating of tribal contacts list
  Outreach to tribes
  Consider NTF presentation

## Slide 5: Fire and Smoke Work Group

## Slide 6: Workplan Progress by Fire and Smoke Work Group
Workplan Progress over the Last Month
  Held workgroup call on 2/24
  FFS EI:
    Contractor wrote a draft final report on fire emissions inventory work for Regional Haze modeling
    Contractor completed preparation of Future Fire Scenario Wildfire and Rx EIs for RH modeling. Data will be sent to Ramboll by the end of this week.
  FETS transition action plan:
    Matt and Tom cooked up a plan to incorporate FETS into Intermountain Data Warehouse platform
    Sara tried to promote FETS revival through communications with NW-AIRQUEST consortium. ID-MT Airshed Group and WA willing to share data.
  Review of final tasks in WRAP workplan:
    Final task is “Wildfire coordination between states, tribes, and feds”
    Tom suggested using the task as a jumping off point to reorganize the workgroup going forward. Plan is to meet quarterly as a discussion group that could cover topics like wildfire coordination, exceptional events, smoke management, air sensors…

## Slide 7: Workplan Progress by Fire and Smoke Work Group
Workplan Tasks for the Next Two Months
  Members to review draft EI report and send Matt feedback
  Matt will revise FETS Action Plan to include new plan to incorporate with IDW
  Draft a list of bullet points to summarize self assessment and outline the future of the workgroup
  Final, valedictory workgroup call will be on April 6.

## Slide 8: Proposed Future Projects - FSWG
Continuing quarterly calls for Fire and Smoke WG (draft bullets)
  Provide a venue for federal, state, and tribal fire and smoke people to discuss matters relevant across agencies
    Wildfire and Rx coordination across agencies and jurisdictions
    Documentation and data sharing for exceptional events due to wildfire or Rx burns
    Maintain a link between regional haze planning and operational fire and smoke people
    Emissions inventory approaches, remote sensing, and other technical issues involving air quality and fire and smoke

## Slide 9: Oil and Gas Work Group

## Slide 10: Workplan Progress by Oil and Gas Work Group
Workplan Progress over the Last Month
  OGWG and Project Management Team (PMT) review and feedback
  Final Revisions (CO & NM information changes): Task 2 – Forecast Scenario (OTB & OTW - Medium Emissions Scenario)
  Final Revisions (CO & NM information changes): Task 2 – Forecast Scenarios (OTB & OTW - Low and High Emissions Scenarios)
  Consensus Approval February 11, 2020: Task 4 – Agency Program Review
  Seeking Consensus Approval: Task 3 – Additional Reasonable Controls
Tasks for the Next Two Months
  OGWG Self-Assessment
  Coordination - Integration for WRAP OGWG Base and Future Year Emissions Inventories in National Collaborative Platform

## Slide 11: Proposed Future Projects - OGWG
Potential Additional Future Project/s
  February 11, 2020 OGWG Bi-Monthly Call initiated Self-Assessment to determine future direction and needs of OGWG in the upcoming year
  OGWG Co-Chairs to discuss best way to seek input from members/advisors
  Additional discussion planned April 14, 2020 OGWG Bi-Monthly Call

## Slide 12: Regional Technical Operations Work Group

## Slide 13: Workplan Progress by RTOWG Work Group
Workplan Progress over the Last Month
  Weekly co-chair coordination calls
  Weekly calls with Ramboll to keep track of modeling progress
  Initial comparison of 1) 2014v2 and 2) representative baseline model results for IMPROVE most impaired days (MID)
Example at Canyonlands for IMPROVE, 2014v2,
and representative baseline on most impaired days

## Slide 14: Workplan Progress by RTOWG Work Group
Workplan Progress over the Last Month
  Transfer of modeling files to CIRA
  Finishing processing of 2028 emissions, should be done by next week
  Weighted Emissions Potential/Area of Influence (WEP/AOI) analysis started
    Trajectory residence time analysis done, need 2028 emissions for WEP

## Slide 15: Workplan Progress by RTOWG Work Group
Workplan Progress over the Last Month
  A series of “Run Specification Sheets” is available for review
    Natural (NAT) and No International (ZROW) GEOS-Chem/CAMx
    RepBase Source Apportionment Modeling (NAT/ANT & U.S./Intl)
    RepBase and 2028 On-the-Books (2028OTB) Modeling
    Dynamic Evaluation: CAMx 2002 Modeling
    WEP/AOI Analysis

## Slide 16: Workplan Progress by RTOWG Work Group
Workplan Tasks for the Next Two Months
  Future year (2028) CAMx simulations
    2028 on-the-books emission controls with 2014 fire emissions
    2028 on-the-books emission controls with representative baseline fire emissions
    2028 potential additional emission controls with representative baseline fire emissions
    2028 adopted additional emission controls with representative baseline fire emissions
    2028 on-the-books emission controls with future wild fire emissions
    2028 on-the-books emission controls with future prescribed fire emissions
    2028 on-the-books emission controls with future boundary conditions
    2028 on-the-books emission controls with 2014 fire emissions (CMAQ – optional)

## Slide 17: Workplan Progress by RTOWG Work Group
Workplan Tasks for the Next Two Months
  Future year (2028) CAMx source apportionment simulation
  Continue development of evaluation tools for emissions and model results
  Calculate and display 2028 Reasonable Progress Goals (RPG)
  Finish WEP/AOI analysis
  Dynamic Model Evaluation

## Slide 18: RTOWG Remaining Workplan Tasks

## Slide 19: Regional Haze Planning Work Group

## Slide 20: Workplan Progress by Regional Haze Planning Work Group
Workplan Progress over the Last Month
  No Large Work Group call in February – Subcommittee calls
Workplan Tasks for the Next Two Months

## Slide 21: Workplan Progress by RH Planning Work Group – Control Measures Subcommittee
Workplan Progress over the Last Month
  February Call discussion on providing emission reduction estimates to WRAP by March 16th deadline
  A few states (AZ, ND & NM) further along in the 4-factor review intend to provide emission reduction estimates for the 2028 control run
  Several states (CO, ID, MT, OR, UT, WA) further behind in the 4-factor review will likely rely on OTB/OTW reductions in the 2028 baseline
  Couple states (CA & NV) may provide emission reduction estimates
Workplan Tasks for the Next Two Months
  States to continue 4-factor review work
  States to review WEP analysis when it becomes available

## Slide 22: Workplan Progress by Coordination and Glide Path Subcommittee
Workplan Progress for February
  TSS FAQ Document Finalized
  TSSv2 Delivery Update Presentation
  ARS Data Substitution and IMRPOVE December Patch Presentation
  Storyboard Update
Workplan Tasks for the Next Two Month
  Continue overview of TSSv2 development
  Gain consensus on TSS Glossary
  Support creation of RH Storyboard
  TSS Prioritization

## Slide 23: Workplan Progress & Coordination by RHPWG Emissions Inventory & Modeling Protocol SC
Workplan Progress over the Last Month
  Coordinated with other subcommittees, states, and contractor as needed to review/update emissions as needed.
  Finalized OTW/OTB emissions inputs from states
  Shared info with states/locals about progress on 4-factor analyses and submitting emissions reductions for the controls scenario modeling inputs
Workplan Tasks for the Next Two Months
  Reports on results of base & future year visibility, source apportionment modeling, and model performance evaluation
  RTOWG contractor-supported report on Reasonable Progress Goals
  RTOWG – contractor supported Weighted Emissions Potential (WEP) analysis that will provide WEP maps of source areas impacting each Class I area

## Slide 24
End of Workplan Progress Update