## Sheet1
| 2018 | 2019 | [11 empty] | 2020
| Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
Shakeout | 2018 Dec: 2014 Base Year Modeling Platform v1 Shakeout - Emissions Processing, Met Modeling/MPE, Global Modeling/MPE, AQ Modeling/MPE, Modeling Plan (RTOWG and contractor team)
Project | 2019 March: 2014 Base Year Modeling Platform v2 and 2013-2017 Representative Baseline Development - Processing of revised Emissions, AQ Modeling/MPE (RTOWG, EI&MP SC, and modeling contractor team)
OGWG Base Year Inventory Development and Finalization
FSWG Base Year Inventory Development
Task 1 | 2018 Dec: Completion of RH Monitoring Data Analysis Round 1 (MGSSC and contractor)
RH Monitoring Data Analysis Round 2 (contractor for MGSSC)
Task 2 | 2019 May: Dynamic Model Evaluations for Regional Haze Progress to Date (RTOWG and contractor team)
Task 3 | 2019 June: Assessment / possible application of data for 2016 & projections - National Collaborative Emissions Modeling Platform (RTOWG and contractor team)
Task 4 | 2019 April: 2023 and 2028 On-the-books Emission Inventory Development (RTOWG, EI & MP SC, and contractor team)
OGWG On-the Books 2028 Inventory Development
OGWG Additonal Reasonable Controls 2028 Inventory Development
FSWG Future Year Inventory Development
Task 5 | 2019 Aug: 2023 and 2028 On-the-books Air Quality Modeling (RTOWG and contractor team)
Task 6 | 2019 Sept: 2028 Source Apportionment/Sensitivity/Control Scenarios Modeling (RTOWG and contractor team)
Task 7 | 2019 May: Data and Documentation Delivery (SDSC with modeling contractor team and IWDW / TSSv2 team)
Detailed 2014 Modeling Platform Development and Shakeout Activities
| 2018 | 2019
| Dec | Jan | Feb | March | April | May | June | July | Aug | Sept | Oct | Nov | Dec
2014 Modeling Platform Shakeout
Task 1 | 2018 Dec: Develop and Finalize Modeling Plan
Task 3 | 2018 Dec: Update 2014 NEI with State comments
Task 7 | 2018 Dec: Single-Source Modeling Webinar and memo
Task 3 | 2019 Jan: 2014 Emissions Modeling and Reporting/Transfer to IWDW
Task 4 | 2019 Jan: 2014 Met Modeling, MPE, and Reporting/Transfer to IWDW
Task 5 | 2019 Jan: Process Global Modeling for BC/Transfer to IWDW
Task 3 | 2019 Feb: 2014 Emissions Summary Reporting
Task 6 | 2019 Feb: 2014 PGM Configuration, MPE, Annual Runs, Sensitivity Testing, and Reporting/Transfer to IWDW
Task 12 | 2019 March: Shakeout Close-out Meeting