## Table 1
Oil and Gas Work Group (OGWG) 2018-2019 Phase II Tasks, Deliverables, Schedule, & OGWG Involvement
Task Description |  | Deliverable Description | Schedule (Months from Project Start (est. 06/18)) | OGWG Involvement^
OGWG Co-Chair Administration & Meetings
Work Group Administration & Meetings |  | Coordination of Bi-Monthly OGWG calls and periodic Project Management Team calls, participation on other O&G calls, posting of materials on OGWG website, and other general planning efforts related to the OGWG. | On-Going | Coordinate and oversee efforts (est. 5-8 hours a month per co-chair)
Contracted Tasks for 2018-2019
Task 1 2014 (Planning) Base Year Emission Inventory
1a | Inventory Compilation, Reconciliation, Data Gaps | Emission Inventory File | 1 | not applicable
1b | 2014 O&G Activity | 2014 O&G Activity File | 1.5 | not applicable
1c | Identify Emission Factors and Speciation Profiles for Oil and Gas Sources | Literature Review PowerPoint | 2.5 | Comment on PPT
|  | Draft and Final O&G Survey | 3.5 | Review Draft, Complete Survey
|  | O&G Survey Results Memorandum | 5.5 | Comment on Memo
1d | Technical Improvements | Draft and Final Emission Inventory | 7 | Review Draft
1e | Reporting | Draft and Final Report | 7 | Review Draft
1f | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 8.5 | not applicable
Task 2 Forecast Year (OTB & OTW Controls) Oil & Gas Emissions Inventory
2a | Identify historical growth, supply, demand, and production decline | Graphs of Historical O&G Activity Trends with O&G Price History | 3 | Comment on Graphs
2b | Identify a Range of Forecast Year Oil and Gas Scenarios | Draft and Final One-page Forecast Scenario Description, 2023 O&G Activity Growth Factors for Three Scenarios | 5.5 | Comment on One- pager, Comment on Graphs
2c | Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | OTB & OTW Emission Controls Matrix | 7 | Collaborate to fill-in matrix
2d | Implement Regionally-Consistent 2023 Forecast (OTB & OTW controls) Emissions Inventory | Methodology Presentation, Draft and Final Emission Inventory | 9.5 | Comment on Presentation, Review Draft Inventory
2e | Reporting | Draft and Final Report | 9.5 | Review Draft
2f | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 10.5 | not applicable
Task 3 Forecast Year (Additional Reasonable Controls) Oil & Gas Emissions Inventory
3a | Identify Additional Reasonable Controls for Oil and Gas Sources | Additional Controls Emission Scenario Memorandum | 11 | Comment on Memo
3b | Identify Rule Penetration and Effectiveness for Oil and Gas Sources: National, State, Local, Tribal | Additional Reasonable Emission Controls Matrix | 14 | Comment on Controls Matrix
3c | Implement Regionally-consistent 2023 Forecast (Additional Reasonable Controls) Emissions Inventory | Methodology Presentation, Draft and Final Emission Inventory | 16 | Review Draft
3d | Reporting | Draft and Final Report | 16 | Review Draft
3e | SMOKE-ready Emission Inventory Files | SMOKE-ready Emission Inventory Files | 17 | not applicable
Task 4 O&G Programs and Emission Management
4a | Identification and Review of Member Agency Oil & Gas Programs | Survey of Existing O&G Programs. Survey Results Presentation. | 13 | Collaborate on Survey Development, Fill-out Survey, Comment on Presentation.
4b | Reporting | Draft and Final Memoranda | 15 | Review Draft
^Bold items will be reviewed by the full OGWG; items in regular font will be reviewed by the OGWG Project Management Team which is a subset of the OGWG.